## Sheet3
Agile Product BackLog
User Story ID | Task Name | Sprint # | Assigned To | Start | Finish | Priority | Status | Story Points | Assigned To Sprint
Sprint 1
1 | Task 1 | 1 | Cici | Week 1 | Week 5 | Low | Complete | 1 | Yes
1 | Task 2 | 1 | Cici | Week 1 | Week 5 | Low | Complete | 0.5 | Yes
1 | Task 3 | 1 | Cici | Week 1 | Week 5 | Low | Complete | 0.5 | Yes
2 | Task 4 | 1 | Cici | Week 1 | Week 5 | Low | Complete | 0.5 | Yes
2 | Task 5 | 1 | Cici | Week 1 | Week 5 | Low | Complete | 0.5 | Yes
3 | Task 6 | 1 | Harrison / Jay | Week 1 | Week 5 | High | Complete | 5 | Yes
3 | Task 7 | 1 | Harrison / Jay | Week 1 | Week 5 | High | Complete | 5 | Yes
4 | Task 8 | 1 | Harrison / Nick | Week 1 | Week 5 | High | Complete | 9 | Yes
5 | Task 9 | 1 | Harrison | Week 1 | Week 5 | High | Complete | 6 | Yes
Sprint 2
6 | Task 10 | 2 | Jay | Week 1 | Week 4 | High | Complete | 4 | Yes
7 | Task 11 | 2 | Jay | Week 1 | Week 2 | Low | Complete | 2 | Yes
7 | Task 12 | 2 | Jay | Week 1 | Week 1 | Low | Complete | 2 | Yes
7 | Task 13 | 2 | jay | Week 1 | Week 4 | Low | Complete | 2 | Yes
8 | Task 14 | 2 | Mohammed/Logan | Week 1 | Week 5 | High | Complete | 8 | Yes
8 | Task 15 | 2 | Mohammed/Logan | Week 1 | Week 5 | High | Complete | 8 | Yes
9 | Task 16 | 2 | Logan/Cici | Week 1 | Week 5 | High | complete | 6 | Yes
9 | Task 17 | 2 | Logan/Cici | Week 1 | Week 5 | High | Complete | 6 | Yes
9 | Task 18 | 2 | Logan/Cici | Week 1 | Week 5 | High | Complete | 6 | Yes
10 | Task 20 | 2 | Jay/Mohammed | Week 1 | Week4 | High | Complete | 6 | Yes
10 | Task 21 | 2 | Jay/Mohammed | Week 1 | Week 4 | High | Complete | 6 | Yes
10 | Task 22 | 2 |  |  |  | High | Complete | 6 | Yes