## Sheet1
AGILE SPRINT 1 BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 2
Create button which can allow user to view customer testimonials |  | Cici | Complete | 2 | 1 | 1 | 0 | 0 | 0 | 0
Provide text box where user can enter their own testimonial |  | Cici | Complete | 2 | 0 | 1 | 1 | 0 | 0 | 0
Save customer testimonial to file |  | Cici | Complete | 2 | 0 | 0 | 0 | 1 | 1 | 0
User Story #2 | 1
Povide button/menu where user can view contact info |  | Cici | Complete | 3.5 | 1 | 1 | 1.5 | 0 | 0 | 0
Add logo and team name |  | Cici | Complete | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0
User Story #3 | 10
Povide button/menu where user can view contact info |  | Harrison/Jay | Complete | 3.5 | 1 | 1 | 1 | 0 | 0 | 0
Add logo and team name |  | Harrison/Jay | Complete | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0
User Story #4 | 9
Display prompt that shapes and text can be moved in GUI window |  | Harrison/Nick | Complete | 15 | 0 | 5 | 5 | 5 | 5 | 0
User Story #5 | 6
As an admin all shapes can be created and removed |  | Harrison | Complete | 5 | 0 | 0 | 0 | 2.5 | 2.5 | 0
TOTAL |  |  |  | 34 | 2 | 9 | 8.5 | 8.5 | 9.5 | 0