## Agile Sprint Backlog - BLANK
AGILE SPRINT 2 BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #6 | 4
Make and keep a file update that tracks all shapes rendered |  | Jay | Complete | 2 | 1 | 0.5 | 0 | 0 | 0 | 0
User Story #7 | 2
Create vector that stores the username and passwords |  | Jay | Complete | 5 | 2 | 0.5 | 1 | 2 | 0 | 0
Hard code username and password |  | Jay | Complete | 1 | 0.5 | 0.5 | 0 | 0 | 0
Give admin more access |  | Jay | Complete | 1 | 0.5 | 0.5 | 0 | 0.5 | 0
User Story #8 | 8
Create drop down menu for the user to see what object they have drawn |  | Mohammed/Logan | Complete | 5.5 | 1 | 1 | 1 | 2 | 1 | 0
Have menu listed in order based on ID,Area or Perimeter |  | Mohammed/Logan | Complete | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0
User Story #9 | 6
If sorted by area Type,ID and Area are only reported |  | Logan/Cici | Complete | 3 | 0 | 0 | 2 | 0.5 | 1 | 0
Include sorting functionality default by ID |  | Logan/Cici | Complete | 2 | 0 | 0 | 0 | 1 | 1 | 0
Include sorting by area functionality |  | Logan/Cici | Complete | 1 | 0 | 0 | 0 | 1 | 1 | 0
User Story #10 | 6
If sorted by parameter Type,ID and Parameter are only reported |  | Jay/Mohammed | Complete | 3 | 0 | 0 | 1 | 1 | 1 | 0
Inlucde sorting functionality defult by ID |  | Jay/Mohammed | Complete | 2 | 0 | 0 | 1 | 0.5 | 1 | 0
Include sorting functionality default by ID |  | Jay/Mohammed | Complete | 1 | 0 | 0 | 0 | 0 | 1 | 0
TOTAL |  |  |  | 27 | 5 | 3 | 6 | 8.5 | 7.5 | 0